## Before odd one issue
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version
comments
mgh-1 |  | background sound is always in same volume while another voice for instruction coming not making more effectiveness. |  | Fixed | Fixed
mgh-2 |  | Instruction's sound coming only one time, no option repeat the game. |  | Fixed | Fixed
mgh-3 |  | if gamer choose the wrong image need to make a sound. |  | Fixed | Fixed
mgh-4 |  | app is closing or crushing while tapping on the cross button. |  | waiting for Pop up UI | not started yet
mgh-5 |  | in first episod, stage - 05 there is a design issue for the left side option. |  | Fixed | Fixed
mgh-6 |  | in the bottom and upper portion in all frame looking cut down. | https://drive.google.com/file/d/1Xs8TNiItqnHNHomhmxShk5n0uAO2c3Hk/view?usp=share_link | Fixed | Fixed | d
mgh-7 |  | while i'm getting time to match the image app not working as logic |  | not found the error...please record a video and show. | not started yet
mgh-8 |  | in all frame parents showing button. | https://drive.google.com/file/d/1Xz3wtKQcqeU_q4R3kCw-qtUm2i5nRF-a/view?usp=share_link | Fixed | Fixed
mgh-9 |  | The stage button UI does not identifiable because all 3 stars are looks the same. I can not identify which stage it is | MGH 9 issue pic | Design Based on PSD | not started yet
mgh-10 |  | When we move the wrong element in the wrong place it takes place in that place it does not go to its own place. | MGH 10 issue pic | No wrong in this question, according to voice, place one slid | not started yet
mgh-11 |  | When we took an element in a hand the element should look like that it took place in hand but now it looks like the element took place behind or front of the hand | MGH 11 issue pic | Fixed | not started yet
mgh-12 |  | We can not move two elements in the same direction. | MGH 12 issue pic | Fixed | not started yet
mgh- 13 |  | A user can not finish the 1st stage level 5 game. was stuck in a loop. |  | Fixed | not started yet
Mgh 14 |  | 1st stage reply button does not work |  | Fixed | not started yet
Mgh 15 |  | In this stage, the instruction is put right to left, but there are 3 elements & do not mention the order. These two elements in the same line which element have to move first its not mention in the element |  | Fixed | not started yet
Mgh 16 |  | Setting button is not working |  | waiting for graphics | not started yet
Mgh 17 |  | Game pause button is not working |  | waiting for graphics | not started yet
Mgh 18 |  | Menu Button does not working |  | waiting for graphics | not started yet
Mgh 19 |  | language medium level porbo 1 stage 2 elements are clash with each other | mgh 19 issue pic | Fixed | Not Fixed((mgh 19 issue img)
Mgh 20 |  | language hard level porbo 1 stage 1 element take place in a wrong position | Mgh 20 issue pic | Fixed | Fixed
Mgh 21 |  | In each level there are 3 porbo, I have to number them 1,2,3 to identify them. Which is did our reference app | mrg 21 issue | Need Graphics | not started yet
Mrg 22 |  | Replay button does not work |  | Fixed | Fixed
Mrg 23 |  | According to UI, there is no box, plz remove it for this type of elements | Mgh 23 issue pic | Fixed | Not Fixed(mgh23 issue pic)
Mgh 24 |  | According to ui the lemon colour should be green but here its yellow | ngh 24 issue pic | Fixed | Fixed
Mgh 25 |  | According to ui, the nashpoti color is not matching. | Mgh 25 issue pic | Fixed | Fixed
Mgh 26 |  | Banana position in the left side it should be right side according to the ui | MGh 26 issue pic | Fixed | Fixed
Mgh 27 |  | After take place naspoti in a hand the half of naspoti was vanish in between the hands | Mgh 27 issue pic | Fixed | Fixed
Mgh 28 |  | In the language game, hard level porbo 3,1st stage missing, there was wrong voice is used |  | Fixed, used Audio No.12 | same for 13 as well
Mgh 29 |  | Many elements are take place in the wrong place in many stages, specially left corner side | Mgh 29 issue pic | Fixed | Fixed
Mgh 30 |  | Medium & hard-level voice color does not match according to the drive design. | Mgh 30 issue pic | Fixed | Fixed
Mgh 31 |  | Parents buttons are missing in all stages. | Mgh 31 issue pic | Fixed | Not Fixed
Mgh 32 |  | In expert porbo 1 & stage 1 the left side background UI is not match & the right side background Colour is light according to the design | Mgh 32 issue pic | Fixed | Not Fixed(mgh 32 issue pic)
Mgh 33 |  | The level count button shapes do not match with design | Mgh 33 issue pic | Fixed | Fixed
Mgh 34 |  | In expert level porbo 2 stage 1 the size of naspoti is not matching to design. Looks small. | Mgh 34 issue pic | Fixed | Fixed
Mgh 35 |  | In hard level porbo 2 stages 3 there is no gap between the 3 elements & the banana element is touching the box border. | Mgh 35 issue pic | Fixed | Not fixed
Mgh 36 |  | In hard level porbo 2 stage 4,5 normally the element are in the box, but the box is missing | Mgh 36 issue pic | Fixed | Fixed
Mgh 37 |  | In hard level porbo 3 stages 1, the voice instruction is totally wrong |  | Fixed, used Audio No.12 | same for 13 as well
Mgh 38 |  | In hard level porbo 3 stages 1,2 the right background is not match to the design | Mgh 38 issue pic | Fixed | Fixed
Mgh 39 |  | In hard level porb 2 stage 2 when nashpoti took place on hands the half of naspoti looks vanish | Mgh 39 issue pic | Fixed | Fixed
Mgh 40 |  | In hard level porb 3 stage 4 the horse legs are looks like coming outside from the frame | Mgh 40 issue pic | Fixed | Fixed
Mgh 41 |  | In matching porbo 1 stage 1 same element is twice used, and an element is missing. | Mgh 41 issue img | Fixed
Mgh 42 |  | According to UI The star & ground are separate. So make the gap between them. | Mgh 42 issue pic | Fixed
Mgh 43 | Parents button | The parents button is not working in any stage |  | will work once, parents UI will receive.
Mgh 44(ref mgh-4) |  | When we click the cross button there are should show an alert pop-up of yes or not | mgh 44 issue img | alert POP up UI needed.
Mgh 45(ref mgh 28,37) |  | In expert level porbo 3 stages 1, plz use 12 no audio to complete this | Use 12 no audio | Fixed, used Audio No.12
Mgh 46 ( ref mgh31) |  | The parents button is added but the button is not working in any stages |  | waiting for Parents UI
Mgh 47(ref mgh32) |  | In expert porbo 1 & stage 1 the left side background UI is not match & the right side background Colour is light according to the design | Mgh 47( ref mgh 32 ) issue pic | Fixed
Mgh 48( ref mgh 35) |  | In hard level porbo 2 stages 3 the alignment of the elements is not right | Mgh 48 issue img | Fixed

## Outline issues
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Error in the game | In the outline game easy stage porbo 1 I put the element in the right direction but it shows me an error. That's why i can not go to the next porbo also | Mgh 001 issue | Fixed
Mgh 002 | Without instruction complete the game | In the outline easy game, porbo 2 stages 4 Without fulfill the instruction the game show complete satus |  | fixed
Mgh 003 | Medium game technical issue | In the outline medium game when we put an element in a right place normally it does not move but here it moves, that's why when we put the same element in that spot the game is finished. But actually, all the elements are not placed in the right place. Its a very big | Mgh 003 issue pic | fixed
Mgh 004 | Right corner catch elemnets | In the outlined game every stage in the left top corner there is a fixed spot where elements can put or we say the area can catch elements. | Mgh 004 issue pic | fixed
mgh-005 | Element fixed in wrong place | In outline hard game in porbo 1 stage 5 one element can put in the wrong place. | Mgh 005 issue pic | fixed
mgh-006 | 2 sound button icon | In the outline hard game in porbo 2 stages 2 there are two voice buttons icon. | Mgh 006 issue | fixed
mgh-007 | 2 sound button icon | In the outline hard game in porbo 2 stages 4 there are two voice buttons icon. | Mgh 007 issue | fixed
mgh-008 | Elements does not picked | In the outline hard game in porbo 2 stages 5 i am trying to set the elemnts in right place but it does not picked. | Mgh 008 issue video | working here
mgh-009
mgh-10

## Odd one issues
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version
comments
Mgh 49 | UI not matching | In the odd game, all stages Ui needs to be fixed ( maximum elements are covered by the other elements It especially happened in updated Android version devices. | Mgh 50 issue pic | please share correct screenshot..it's matching screenshot since comment about odd one. | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 50 | The complete pop up missing | in the odd game after completing the porbo 1 stage 5 the pop-up of complete with sound is missing. |  | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 51 | Wrong elements does not show error | In the odd game porbo 1 stage 5, the wrong elements are taking place on the wrong side according to the UI. But it passes the stages. Does not show any error. | Mgh 51 issue pic | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 52 | Wrong sound in right matching | In the odd game porbo 1 stage 5, in right matching it plays the wrong sound & on the other hand in wrong matching it also play wrong sound but on both condition it pass the stages |  | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 53 | Sound comes lately | In the odd game stage, 3,4,5,7,8,9,10 sound comes lately & the sound volume is low |  | Audio file fault.. | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 54 | The complete pop up missing | in the odd game after completing the porbo 2 stage 5 the pop-up of complete with sound is missing. |  | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 55 | Elements are in the wrong place | In the odd game porbo 3 stage 1, elements are took place in the wrong position | Mgh 55 issue pic | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 56 | Elements are in the wrong place | In the odd game porbo 1 stage 1, elements aare takingplace in the wrong position | mgh 56 issue pic | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 57 | Mugdho title missing | On the home page, the mugdho title name is missing | Mgh 57 issue pic | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 58 | UI need to change | The full game UI needs to adjust for the updated android devices. Those devices' elements collapse with one & another elements. Some buttons are cut off like the parents button & cross button. This problem is for the whole game in every stage | Mgh 58 issue video | Okay...will fix in upcoming update...probably..mgh-apk-008 | Give the video. In the latest device, the ui looks zoomed in. I also mention the problem in the video. So plz also listen to it. Hope it helps you to understand the problem |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 59 | Remove the elemnt | In odd game medium porbo 3 stages 5, Plz remove the selected element. | MGh 59 issue pic | element is design based on PSD.. | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 60 | The elements can not move | Once elements take place in the right spot they can not move. if the elements are wrong then it does not accept them. | Mgh 60 issue pic | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 61 | The game was paused | In the odd game medium after finishing the game the finished pop is not showing & the game is gone in a paused mode. Even if it does not go to the home page also. |  | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
MGh 62 | The command sound problem | In odd game expert porbo 1 stage 1 command sound |  | Audio File fault.. | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 63 | Wrong pop up show | Without finished the game the complete pop up is showing | Mgh 63 issue pic | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 64 | Pop up is not showing | In the odd expert game, the finished pop-up is not showing. |  | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
Mgh 65 | Game auto start | After finishing the odd expert level it goes to the home page but here the game is auto start again from the easy level |  | Fixed | Not Started yet |  | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link

## Resource issue
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Need a different porbo logo | In a single game, there are mainly 3 porbo, so I need 3 different porbo UI with counting the stage number. |  | need UI
Mgh 002 | Change the voice command | In the outline game, medium porbo 2 stages 1 voice does not suit the scenario. It should be changed.
Mgh 003 | Change the voice command | In the outline game, medium porbo 2 stages 1 voice does not suit the scenario. It should be changed.
Mgh 004 | Change the voice command | In the outline game, hard porbo 2 stages 3 voice does not suit the scenario. It should be changed.
Mgh 005 | Change the voice command | In the outline game, hard porbo 2 stages 5 voice does not suit the scenario. It should be changed.
Mgh 006
Mgh 007
Mgh 008
Mgh 009
Mgh 010
Mgh 011
Mgh 012
Mgh 013
Mgh 014
Mgh 015
Mgh 016
Mgh 017
Mgh 018
Mgh 019
Mgh 020
Mgh 021 | wrong sound not happend in episode 5 | In 1st stge , 5th episode when player try to put wrong slider its not give any wrong sound or alert | MghRes021 | fixed
Mgh 022 |  | In 1st stage, 5th episode big slider fit on small slider place which is not suppose to happen | MghRes022 | fixed
Mgh 023 |  | in stage 2 , 1st episode ripe mango picture are rotate (accoring to design ). | MghRes023 | fixed
Mgh 024 |  | In stage 3 , lion size i not matching with resoures. | MghRes24 | fixed
Mgh 025
Mgh 026
Mgh 027
Mgh 028
Mgh 029
Mgh 030
Mgh 031
Mgh 032
Mgh 033
Mgh 034
Mgh 035
Mgh 036
Mgh 037
Mgh 038

## Backlog issues
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
mgh-1 | slider is behind the hand | In 1st episode 1st stage, when player try to put a slider on the hand it looks the slider is behind the hand | mgh-1 | fixed...coming in next apk. |  |  |  | these are the previous issues which were soved before but in new update those issues are arising again. so if this repeating again we both faces problem like time consuming. and it also effect on your reputation.
mgh-2 | not matching with instration | In 1st episode 1st stage ,player supose to put one slider on hand according to instruction but now player can also put 2 slider. | mgh2 | fixed...coming in next apk.
mgh-3 | close button did not give any pop up | when user click close button it not giving any" do you want to close ?" pop up , its automatically closed and user has to start from the begin. | mgh3 | fixed...coming in next apk.
mgh-4 | picture rotate in stage 1 , episode 2 | In 1st episode 2nd stage two slide picture are rotate not matching with the deisgn picture | mgh4 | fixed...coming in next apk.
mgh-5 | picture rotate in stage 1 , episode 2 | In 1st episode 2nd stage when player put one slider on hand its not matching with design picture | mgh5 | fixed...coming in next apk.
mgh-6 | position is not match | In 1st episode, 5th stage , when user try to put small slider sometime the postion is not ok | mgh6 | fixed...coming in next apk.
mgh-7 | background color should be more white | In 2nd episode , fruits indentifiers hand background supose to be more white according to design. | mgh7 | fixed...coming in next apk.
mgh-8 |  | After compleated 2nd episode when player wants to click "replay" instead of going 2nd episode again it start from 1st level again. |  | fixed...coming in next apk.
mgh-9 |  | In episode 2, stage 5 when player once change the fruits position, all the fruits are overlap one another. | mgh9 | fixed...coming in next apk.
mgh-10 |  | In episode 2 and 3 , some stages there is a perticular place where all the element are stucking | mgh10 | fixed...coming in next apk.
mgh-11 |  | In episode 3, where all the elements have to put that background is more white and not match with figma . | mgh11 | fixed...coming in next apk.
mgh-12
mgh-13
mgh-14
mgh-15
mgh-16
mgh-17
mgh-18
mgh-19
mgh-20
mgh-21
mgh-22
mgh-23
mgh-24
mgh-25
mgh-26
mgh-27
mgh-28
mgh-29
mgh-30
mgh-31
mgh-32
mgh-33
mgh-34
mgh-35
mgh-36
mgh-37
mgh-38
mgh-39

## patching game
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Element took place in wrong position | In porbo 1 stage 2 elements took place in the wrong position. Please fix it. | Mgh 001 issue pic | Fixed..upcoming APK..
Mgh 002 | Elements is cut off from the mobile screen | In porbo 1 stage 3 some parts of the elements are cut off from the mobile screen. this looks very bad. | Mgh 002 issue pic | Fixed..upcoming APK..
Mgh 003 | Elements are moving | In porbo 1 stage 3,4,5 elements are moving after putting the elements in the right spot. | Mgh 003 issue pic | Fixed..upcoming APK..
Mgh 004 | Technical issue. | In the porbo 1 stage, 3,4,5 elements are moving but there is also another issue a user can finish the game by moving one element only. It's a big bug. Please fix it. | Mgh 004 issue pic | Fixed..upcoming APK..
Mgh 005 | Remain a gap | In porbo 2 stage 1,2 there is remain a gap after putting the elements. | Mgh 005 issue pic | Fixed..upcoming APK..
Mgh 006 | Screen Zoom in | In porbo 2 stages 2,3,4,5 the mobile screen is again zoomed in, as a result, the parents & cross buttons are gone out of the frame. Looks very bad. This type of issue is repeating which is not bad. |  | Fixed..upcoming APK..
Mgh 007 | Technical issue. | In the porbo 3 stage 5 elements are moving but there is also another issue a user can finish the game by moving one element only. |  | Fixed..upcoming APK..
Mgh 008 | Cover one element to another | In the medium game, porbo 1 stage 2 elements cover the parent's button. Please solve this issue. | Mgh 008 issue pic | Fixed..upcoming APK..
Mgh 009 | moving Elements view not Good | In the Hard game of patching when elements are moved through another element it looks like passing elements move middle of that element but it normally looks like it passes over those elements. | Mgh 009 issue pic | Fixed..upcoming APK..
Mgh 010 | Elements crash | Here elements clash with one another elements. | Mgh 10 pic | Fixed..upcoming APK..
Mgh 011 | Remain a gap | In porbo 3 stage 1 there is remain a gap bellow after putting the elements. |  | Fixed..upcoming APK..
Mgh 012 | Common Issues | In this game, there is some common issue that is repeated in every stage. Mobile UI is zoomed in, Finished the game by moving just one element again & again. when an element is put in the right spot it does not move but here it can move which is wrong. Sometimes elements crash with one & another. We need to check those points because these issues are repeating in every stage. Please Solve those issues |  | Fixed..upcoming APK..

## Feedback On apk 9
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Home page button issue | On the homepage, buttons are too much close to the border of the mobile screen which looks bad. please bring the buttons a little bit down. |  | fixed
Mgh 002 | Sound off button missing | In the setting button sound off button is missing. |  | fixed
Mgh 003 | Buttons are not smmotth | The homepage button is not smooth.
Mgh 004 | Pop up position | We need to change the pop-up position of the homepage buttons. When we click the button the pop can show under that button not middle of the home screen. |  | fixed
Mgh 005 | Elements took the wrong place. | In the patching game porbo 1 stage 1, the elements took the wrong place. | Mgh002 issue pic i | fixed
Mgh 006 | Change the pop notification | When we click the cross button it shows do you want to close? Please add something. Do you want to close the game? |  | fixed
Mgh 007 | Yes button not working. | when we click the cross button it shows pop up. In that pop, there are two buttons yes and not. The Yes button is not working. |  | fixed
Mgh 008 | Cover one element to another | In the patching game porbo 1 stage 1, elements took place in the right spot but the game does not proceed to the next level. It freezes. Elements also move after putting in the right spot. which is not correct | Mgh 008 issue pic | fixed
Mgh 009 | Elements took the wrong place. | In the patching medium game porbo 2 stages 3,4,5 the elements took the wrong place. | Mgh009 issue | fixed
Mgh 010 | Elements took the wrong place.&game become pause | In the outline game porbo 1 stage 1 element took place in the wrong position. | Mgh010 issue pic | fixed
Mgh 011 | Elements took the wrong place.&game become pause | In the outline game porbo 1 stage 2 element took place in the wrong position. | Mgh011 pic | fixed
Mgh 012 | Elements took the wrong place.&game become pause | In the outline game porbo 1 stage 3 element took place in the wrong position. | MGh012 issue pic | fixed
Mgh 013 | Elements took the wrong place.&game become pause | In the outline game porbo 1 stage 4,5 elements took place in the wrong position. | Mgh 013 issue pic | fixed
Mgh 014 | Elements took the wrong place.&game become pause | In the outline game porbo 2 stage 1 elements took place in the wrong position. | MGH014 issue pic | fixed
Mgh 015 | Repeat Issue | Look like a pattern. A similar type of issue is found in every stage of the game. Therefore I can see a pattern in this issue. Elements took place in 2 wrong positions. The positions are left most downside & right most upper side. Those position elements are taking place. It's happened at almost every stage. So please check this issue for all stages. This issue is repeating. |  | fixed

## Feedback On apk 10
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Notification issue | Cross-button notifications should show the middle of the screen. | Mgh001 | Fixed.
Mgh 002 | Menu Cross button | In the menu option, the cross button is not smooth. Sometimes the click does not work then try multiple times then it works. The size of the cross button needs to increase a little more. | Mgh002 | Fixed.
Mgh 003 | Setting cross button | In the setting option, the cross button is not smooth. Sometimes the click does not work then try multiple times then it works. The size of the cross button needs to increase a little more. |  | Fixed.
Mgh 004 | Double parents button | On the level page, there is two parents button. | Mgh004 | Fixed.
Mgh 005 | Elements took the wrong place.(Unsolve issue of apk 9) | on the patching easy porbo, 1 level 2 elements are took place in the wrong position. | Mgh005 | Fixed.
Mgh 006 | Setting music on/off button issue | On the patching easy porbo, 2 all stages the music on/ off button is not working. | Mgh006 | Fixed.
Mgh 007 | Elements gap | On the patching of Porbo 2 at all stages, there is a gap between the elements of the bug which is not looking nice. | Mgh 007 | graphics fault, but still i've fixed. :)
Mgh 008 | Elements took the wrong place.(Unsolve issue of apk 9) | on the patching easy porbo, 2 level 3 elements took place in the wrong position. | Mgh008 | Fixed
Mgh 009 | Image gap | On the patching easy porbo 1 level 1-5, there is a gap in all the images. After completing the image the gap is a clear show which does not look good please fix it. | Mgh009 | Fixed.
Mgh 010 | Elements took the wrong place.(Unsolve issue of apk 9) | on the patching easy porbo, 2 level 3,4, 5 elements took place in the wrong position. | Mgh10 | Fixed.
Mgh 011 | Same stage | on the patching easy porbo, 2 levels 3,4 use the same logo as stage 3. stage 4 image is missing | Mgh11 | Fixed.
Mgh 012 | elements conflict | on the patching easy porbo, 3 levels 5 elements are in conflict with other elements. On the left side, there are huge gaps but the lower elements conflict with the border line which is not looks good. | mgh12 | Fixed.
Mgh 013 | Image gap | On the patching medium porbo 1 level 1-5, there is a gap in all the images. After completing the image the gap is clear show which does not look good please fix it. | Mgh13 | Fixed.
Mgh 014 | Image gap | On the patching medium porbo 3 level 1-5, we can see the border lines in all the images. After completing the image the border is a clear show which does not look good please fix it. | mgh14 | Fixed.
Mgh 015 | Image gap, elements conflict | On the patching hard porbo 1 level 1-5, we can see the border lines in all the images. there is also some gap after completing the image. There are also some conflicts between the heart & images | mgh15 | Fixed.
Mgh 016 | Give a wrong background sound | On the patching hard porbo 2 level 3-5, it gives an error sound after finishing the game, please listen to it & fix the issue. |  | Fixed.
Mgh 017 | Image gap | On the patching hard porbo 3 level 1-5, there is a gap in all the images. After completing the image the gap is clear show which does not look good please fix it. | mgh17 | Fixed.
Mgh 018 | Resume button | The resume button is mainly used if they try to pause this app & try to go out from the app. when they come they can continue the game from the resume stage. But here it does not work like that if a user goes out from the app the resume button is not working, it just works for that moment so please change this. | mgh18 | don't close the applicaiton, it will not resume. once user go out without closing the app, it's pause by default and once user get back to app again, it's resume by default
Mgh 019 | Menubar possition | Menubar pop up will show in the middle. | mgh19 | fixed
Mgh 020 | Settings bar possition | Setting bar pop-up will show in the middle. | Mgh 20 | fixed
Mgh 021 | Change the porbo logo | In the whole game please change the porbo logo. Please change it in all the porbo & all the stages. You got this graphics file in the stage folder. Please check it. link is also given in the image link | mgh21 | https://drive.google.com/drive/folders/1fRIuQrXJmez9hseqT_auZPrygag-kXJd |  | Updated
Mgh 022 | Cross button possition | Cross bar pop-up will show in the middle. | mgh 22 | fixed
Mgh 023 | Elements took the wrong place.(Unsolve issue of apk 9) | In the language game easy porbo 1 stage 1, the elements are taking place in the wrong position also some elements have clashed with other elements. as result some elements do not look properly. | Mgh 023 | fixed
Mgh 024 | UI looks different(Unsolve Issue) | In android version 10 the UI looks perfect but in android version 12 it looks not good. In android 12 it looks like zoom in. As a result, elements conflict with other elements. It happened mainly in all the stages of the game. I give a demo example scenario in the screenshot.It's a big issue. please take this issue as a high priority to fix properly. | mgh 024 | Testing under process on different version of android....fixed
Mgh 025 | Voice missing | In the language game easy porbo 2 stages 1 the voice is missing. |  | fixed
Mgh 026 | Repeat voice not working | In the language game medium porbo 1 stage 1 the voice is working on 1st time after that if I click to repeat hear it it does not work. |  | fixed
Mgh 027 | image issue | In the language game medium porbo 2 stage 4 the ball looks going deep in his hand which is not a normal look. | Mgh27' | fixed
Mgh 028 | Voice late issue | In the language game medium porbo, 3 stages 3,4 the voice comes lately. When I click it starts lately |  | audio file fault...please send me proper voice file.
Mgh 029 | Elements took the wrong place.(Unsolve issue of apk 9) | In the language game medium porbo 3 stages 4 the elements are taking place in the wrong position | MGh29 | fixed
Mgh 030 | Elements took the wrong place.(Unsolve issue of apk 9) | In the odd one game easy porbo 1 stage 1 the elements are taking place in the wrong position |  | fixed
Mgh 031 | Elements are missing | On the matching game porbo 1 stage 2-4. perfect elements are missing. It's mainly our design fault. We add those new designs to our drive. So you can fix this issue easily. Here one full element will choose not a single element. The drive link is given. folder name is car stage | Updated | https://drive.google.com/drive/folders/1G5u1kqKMlIx4xEk-1omuchMkXrvPPhLy |  | Updated
Mgh 032 | Elements took the wrong place.(Unsolve issue of apk 9) | In the language game hard porbo 1 stages 3 the elements are taking place in the wrong position | MGh32 | Working fine here.
Mgh 033 | Alignment not right | In the language game hard porbo 1 Stage 5 the element's border alignment is not right need to fix | MGh33 | Fixed
Mgh 034 | Voice missing | In the language game hard porbo 2 Stage 1 the voice is missing. 1st time it works then it does not work |  | Fixed
Mgh 035 | Alignment not right | In the language game hard porbo 2 Stage 3 the element's border alignment is not right and needs to fix. | Mgh34 | Fixed
Mgh 036 | Elements took the wrong place.(Unsolve issue of apk 9) | In the language game hard porbo 2 stages 4 the elements are taking place in the wrong position | MGH 36 | Fixed
Mgh 037 | Alignment not right | In the language game hard porbo 2 Stage 5 the element's border alignment is not right and needs to fix. | 37 | Fixed
Mgh 038 | Swap the element position | In the language game hard porbo 3 Stage 1 According to the voice command need swap the elements so please swap the position of the element | 38 | Fixed
Mgh 039 | Elements took the wrong place.(Unsolve issue of apk 9) | In the language game hard porbo 3 Stages 2 the elements are taking place in the wrong position. As command, there will be a cow in this position, not a goat | 39 | Fixed
Mgh 040 | Elements took the wrong place.(Unsolve issue of apk 9) | In the language game hard porbo 3 Stages 3 wrong elements took place. According to the voice command need to change it. According to the voice, it will be a cow & goat. But here the wrong elements took that position, Please change this | 40 | Fixed
Mgh 041 | Element wrong position | In the language game hard porbo 3 Stages 5 the tiger should take place in the cage, not in the sky looks odd. | 41 | Fixed
Mgh 042 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game easy porbo 1 Stage 1 elements are taking wrong place. | 42 | Don't Place Object at the Edge of mobile.
Mgh 043 | Elements is not smooth | In the Outline game, easy porbo 1 Stage 2 the mark portion is not smooth. The maximum time it fails to move these elements. | 43 | Fixed
Mgh 044 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, easy porbo 1 Stage 3 elements are took place in a wrong position. | 44 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 045 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, easy Porbo 1 Stage 4 elements took place in the wrong position. | 45 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 046 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, easy Porbo 2 Stage 3 elements took place in the wrong position. | 46 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 047 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, easy Porbo 2 Stage 4 elements took place in the wrong position. | 47 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 048 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, easy Porbo 2 Stage 5 elements took place in the wrong position. This is a similar type of issue please fix this issue in the next update & make sure that this issue does not arise again. | 48 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 049 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, easy Porbo 3 Stage 2 elements took place in the wrong position. | 49 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 050 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, easy Porbo 3 Stage 3 elements took place in the wrong position. | 50 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 051 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, medium Porbo 1 Stage 1 elements took place in the wrong position. | 51 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 052 | Elements took the wrong place.(Unsolve issue of apk 9) | In the Outline game, medium Porbo 1 Stage 2 elements took place in the wrong position. | 52 | Don't Place Objects at the Edge of the mobile. Any Reason behind it? This game is developed for the special child. Why we do not place the elements on the edge of the mobile?
Mgh 053
Mgh 054
Mgh 055
Mgh 056
Mgh 057
Mgh 058
Mgh 059
Mgh 060
Mgh 061
Mgh 062

## Feedback On apk 11
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Stage Missing | In the language game, all the game type choosing option is missing |  | it's for testing purpose.
Mgh 002 | UI Does not fix ( Previous Issue) | Still, the UI is not fixed. Some elements conflict with other elements. Especially in the language game porbo 1 porjai 4 elements are & the porbo logo conflict with each other. | MGH 1 | Fixed
Mgh 003 | UI Does not fix ( Previous Issue) | Still, the UI is not fixed. Some elements conflict with other elements. Especially in the language game porbo 1 porjai 1 elements are & the porbo logo conflict with each other. | MGH 2 | Fixed
Mgh 004 | UI Does not fix ( Previous Issue) | Still, the UI is not fixed. Some elements conflict with other elements. Especially in the language game porbo 1 porjai 5 elements are & the porbo logo conflict with each other. | MGH 3 | Fixed
Mgh 005 | Parents Option | in the parents verify option you always give same question 4*4 . It will be changing all time. You can use 10- 15 question. Then rotate them. |  | New
Mgh 006 | Resume Button | I need a proper resume button where i can pause my game & get out of the app. Then when i get into the the game then i can play from that stage i leave the game. Its not to be good that if i leave the game then continue from the first. As a gamer perseptence its borring & irrititing |  | Not Fixed..it's not pause and resume..it's saving and loading features.
Mgh 007 | Game Is not Finshed.( Previous Issue) | After reaching Porbo 2 porjai game is paused. It does not go to the next stage. |  | Need Video...since it's working fine here.
Mgh 008 | Warning Sound Missing | In the matching game, easy porbo 1 porjai 1 the warning sound is not working when I place the wrong elements. It just sounds once then stop. This problem arises sometimes | MGH 8 | Need Video...since it's working fine here.
Mgh 009 | Game Is not Finshed.( Previous Issue) | In the matching game easy After reaching Porbo 1 porjai 1 game is paused. It does not go to the next stage.. It just sounds once then stop. This problem arises sometimes |  | Need Video...since it's working fine here.
Mgh 010 | Device UI issue | The same screen but looks different on a different device. This is happening in every porjai of the game. | MGH 10 | Fixed
Mgh 011 | Elements conflict issue | In the matching game easy porbo 1 porjai 2 elements are conflict with each other. | MGH 11 | Fixed
Mgh 012 | Elements conflict issue( Previous Issue) | In the matching game, easy porbo 1 porjai 3 elements are conflict with each other. | MGH 12 | Fixed
Mgh 013 | Elements conflict issue( Previous Issue) | In the matching game, easy porbo 1 porjai 4 elements are conflict with each other. | MGH 13 | Fixed
Mgh 014 | Elements conflict issue( Previous Issue) | In the matching game, easy porbo 1 porjai 5 elements are conflict with each other. | MGH 14 | Fixed
Mgh 015 | elements are not raking place | In the matching game medium porbo 1 porjai 1 elements are not taking place. it give wrong sound even i put right elements. As a result i can not complete the game also not go to the next level. | MGH 15 | Match the car...put the yellow car in to box...Please check the Reffernce image.
Mgh 016 | Elements conflict issue( Previous Issue) | In the matching game, hard porbo 1 porjai 1 elements are conflict with each other. | MGH 16 | Fixed
Mgh 017 | Elements conflict issue( Previous Issue) | In the matching game, hard porbo 1 porjai 3 elements are conflict with each other. | MGh 17 | Fixed
Mgh 018 | Elements conflict issue( Previous Issue) | In the matching game, hard porbo 1 porjai 4 elements are conflict with each other. | MGh18 | Fixed
Mgh 019 | Full UI Wrong emeplement | In the matching game, hard porbo 2 porjai 1, look at the main UI, It's fully changed. the main elements are missing. As a result, i am stop in this stage & also can not go to the next stage. | MGH 19 | Fixed
Mgh 020 | Elements conflict issue( Previous Issue) | In the odd one game, easy porbo 1 porjai 1 elements conflict with each other. | MGh 20 | Fixed
Mgh 021 | Elements conflict issue( Previous Issue) | In the odd one game, easy porbo 1 porjai 4 elements conflict with each other. | MGH 21 | Fixed |  | Updated
Mgh 022 | Elements conflict issue( Previous Issue) | In the odd one game, easy porbo 1 porjai 5 elements conflict with each other. | MGh 22 | Fixed
Mgh 023 | wrong element placement | In the odd one game, easy porbo 1 porjai 5 wrong elements are take place in the right place | MGh 23 | Fixed
Mgh 024 | Elements conflict issue( Previous Issue) | In the odd one game, easy porbo 1 porjai 5 elements conflict with each other. | 24 | Fixed
Mgh 025 | Elements conflict issue( Previous Issue) | In the odd one game, easy porbo 3 porjai 2 elements conflict with each other. | 25 | Fixed
Mgh 026 | Elements conflict issue( Previous Issue) | In the odd one game, easy porbo 3 porjai 4 elements conflict with each other. | 26 | Fixed
Mgh 027 | Elements conflict issue( Previous Issue) | In the odd one game, easy porbo 3 porjai 2 elements conflict with each other. | 27 | Fixed
Mgh 028 | Elements conflict issue( Previous Issue) | In the odd one game, medium porbo 1 porjai 1 elements conflict with each other. | 28 | Fixed
Mgh 029 | Elements conflict issue( Previous Issue) | In the odd one game, medium porbo 1 porjai 2 elements conflict with each other. | 29 | Fixed
Mgh 030 | Elements conflict issue( Previous Issue) | In the odd one game, medium porbo 1 porjai 3 elements conflict with each other. | 30 | Fixed
Mgh 031 | Elements conflict issue( Previous Issue) | In the odd one game, medium porbo 1 porjai 4 elements conflict with each other. | 31 | Fixed |  | Updated
Mgh 032 | Elements conflict issue( Previous Issue) | In the odd one game, medium porbo 1 porjai 5 elements conflict with each other. | 32 | Fixed
Mgh 033 | Elements conflict issue( Previous Issue) | In the odd one game, medium porbo 1 porjai 5 elements conflict with each other.After finishes it conflict with pop up | 33 | Fixed
Mgh 034 | next Button is not working | In the odd one game, medium porbo 1 porjai 5 the next button is not working as a result i can not go to the next stage | 34 | Fixed
Mgh 035 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 1 porjai 1 elements conflict with each other. | 35 | Fixed
Mgh 036 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 1 porjai 2 elements conflict with each other. | 36 | Fixed
Mgh 037 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 1 porjai 5 elements conflict with each other. | 37 | Fixed
Mgh 038 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 1 porjai 5 elements conflict with each other.After finishes it conflict with pop up | 38 | Fixed
Mgh 039 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 2 porjai 1 elements conflict with each other. | 39 | Fixed
Mgh 040 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 2 porjai 2 elements conflict with each other. | 40 | Fixed
Mgh 041 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 2 porjai 4 elements conflict with each other. | 41 | Fixed
Mgh 042 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 2 porjai 5 elements conflict with each other.After finishes it conflict with pop up | 42 | Fixed
Mgh 043 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 3 porjai 1 elements conflict with each other. | 43 | Fixed
Mgh 044 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 3 porjai 2 elements conflict with each other. | 44 | Fixed
Mgh 045 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 3 porjai 3 elements conflict with each other. | 45 | Fixed
Mgh 046 | Elements conflict issue( Previous Issue) | In the odd one game, hard porbo 3 porjai 4 elements conflict with each other. | 46 | Fixed
Mgh 047 | Elements conflict issue( Previous Issue) | In the outlined game, easy porbo 1 porjai 2 elements conflict with each other. | 47 | Fixed
Mgh 048 | Elements conflict issue( Previous Issue) | In the outlined game, easy porbo 1 porjai 3 elements conflict with each other. | 48 | Fixed
Mgh 049 | Elements conflict issue( Previous Issue) | In the outlined game, easy porbo 1 porjai 4 elements conflict with each other. | 49 | Fixed
Mgh 050 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 1 porjai 1 elements conflict with each other. | 50 | Fixed
Mgh 051 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 1 porjai 2 elements conflict with each other. | 51 | Fixed
Mgh 052 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 1 porjai 3 elements conflict with each other. | 52 | Fixed
Mgh 053 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 1 porjai 4 elements conflict with each other. | 53 | Fixed
Mgh 054 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 2 porjai 4 elements conflict with each other. | 54 | Fixed
Mgh 055 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 2 porjai 3 elements conflict with each other. | 55 | Fixed
Mgh 056 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 2 porjai 4 elements conflict with each other. | 56 | Fixed
Mgh 057 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 2 porjai 5 elements conflict with each other. | 57 | Fixed
Mgh 058 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 3 porjai 1 elements conflict with each other. | 58 | Fixed
Mgh 059 | Elements conflict issue( Previous Issue) | In the outlined game, medium porbo 3 porjai 2 elements conflict with each other. | 59 | Fixed
Mgh 060 |  | In the outlined game, medium porbo 3 porjai 3 elements conflict with each other. | 60 | Fixed
Mgh 061 |  | In the outlined game, medium porbo 3 porjai 4 elements conflict with each other. | 61 | Fixed
Mgh 062 |  | In the outlined game, medium porbo 3 porjai 5 elements conflict with each other. | 62 | Fixed
Mgh 063
Mgh 064
Mgh 065
Mgh 066
Mgh 067
Mgh 068

## Feedback On apk 12
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Parents Button | On the parent's button, the math quiz is missing. It can accessible with one click. |  | Done
Mgh 002 | Save Button | In the parent's button, there should be a save button. After changing the setting parents can save it. |  | Done
Mgh 003 | setting not updated | When I try to update the setting after getting back from the page update does not work. the settings become as default as it is. | 3 | Fixed
Mgh 004 | Elements fixing issue | In the language game easy porbo 2 porjai 4 in a first attempt all the elements are ok, but when it finshed it a elements take place in a wrong possition | 4 | Fixed
Mgh 005 | voice issue | In the language game easy porbo 2 porjai 5 the direction sound is not repeated. It only works once. |  | Fixed
Mgh 006 | voice issue | In the language game medium porbo 1 porjai 5 the direction sound is not repeated. It only works once. |  | Fixed
Mgh 007 | UI Issue | In the patching game Porbo 1 porjai 1 two elements conflict. | 7
Mgh 008 | UI Issue | In the patching game, Porbo 1 porjai 2 in the image border should be all over the image. some part borders showing some parts are missing. It's not looking good. | 8
Mgh 009 | UI Issue | In the patching game, Porbo 1 porjai 3 the image border should be aline & also the border should be showing all the parts. not some of the parts. | 9
Mgh 010 | UI Issue | In the patching game, Porbo 1 porjai 4 in the image border should be all over the image. some part borders showing some parts are missing. It's not looking good. | 10
Mgh 011 | UI Issue | In the patching game, Porbo 1 porjai 5 in the image border should be all over the image. some part borders showing some parts are missing. It's not looking good. Here also some other issues there is a gap in the image & also conflict between the two images. | 11
Mgh 012 | UI Issue | In the patching game, Porbo 2 porjai 3 two elements conflict. which is not looking good. | 12
Mgh 013 | UI Issue | In the patching game, Porbo 2 porjai 4 two elements conflict. which is not looking good.
Mgh 014
Mgh 015
Mgh 016
Mgh 017
Mgh 018
Mgh 019
Mgh 020
Mgh 021 | [5 empty] | Updated
Mgh 022
Mgh 023
Mgh 024
Mgh 025
Mgh 026
Mgh 027
Mgh 028
Mgh 029
Mgh 030
Mgh 031 | [5 empty] | Updated
Mgh 032
Mgh 033
Mgh 034
Mgh 035
Mgh 036
Mgh 037
Mgh 038
Mgh 039
Mgh 040
Mgh 041
Mgh 042
Mgh 043
Mgh 044
Mgh 045
Mgh 046
Mgh 047
Mgh 048
Mgh 049
Mgh 050
Mgh 051
Mgh 052
Mgh 053
Mgh 054
Mgh 055
Mgh 056
Mgh 057
Mgh 058
Mgh 059
Mgh 060
Mgh 061
Mgh 062
Mgh 063
Mgh 064
Mgh 065
Mgh 066
Mgh 067
Mgh 068

## Feedback On apk 13
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | parents Button issue | After the first installation parents button is not working. It shows time over. after getting out from that page the parent's button is not working. After quilting the whole app then it works which is not right. | 1 | Done
Mgh 002 | Button conflict. | On the parent's page cross button & save button are conflicted. You can shift the save button behind the settings button. | 2 | Done
Mgh 003 | Notification missing | After click the save button there should be showing a notification that " the data is saved/ updated " |  | Fixed
Mgh 004 |  | In the patching game Porbo 1 porjai 1 two elements conflict. | 4 | Fixed
Mgh 005 |  | In the patching game, Porbo 1 porjai 2 in the image border should be all over the image. some part borders showing some parts are missing. It's not looking good. | 5 | Fixed
Mgh 006 |  | In the patching game, Porbo 1 porjai 3 the image border should be aline & also the border should be showing all the parts. not some of the parts. | 6 | Fixed
Mgh 007 |  | In the patching game, Porbo 1 porjai 4 in the image border should be all over the image. some part borders showing some parts are missing. It's not looking good. | 8 | Fixed
Mgh 008 |  | In the patching game, Porbo 1 porjai 5 in the image border should be all over the image. some part borders showing some parts are missing. It's not looking good. Here also some other issues there is a gap in the image & also conflict between the two images. | 9 | Fixed
Mgh 009 |  | In the patching game, Porbo 2 porjai 3 two elements conflict. which is not looking good. | 10 | Fixed
Mgh 010 |  | In the patching game, Porbo 2 porjai 4 two elements conflict. which is not looking good. | 11 | Fixed
Mgh 011 |  | In the patching game, Porbo 2 porjai 5 two elements conflict. which is not looking good. | 12 | Fixed
Mgh 012 |  | In the patching game, Porbo 3 porjai 1 elements are in conflict with others elements. | 13 | Fixed
Mgh 013 | adult verify | In the adult verify page submit button is not working.it happenend some times. Not in. every time. |  | Fixed
Mgh 014 | technical issue | In the setting when we select the number from maximum games can be played,it also working on game selection also. As a example if i select 1 game can be played than we can add only one game which can be language game or matching game or outline game. But i can not add 2 or 3 game when i select 1 game. |  | This is what it's functionality about, once user select max limit 1, then he can choose only one slot among of 5, if he want to choose three then he has to select 3 number from drop down list. | But Main problem is limit & selection does not match. Its have to match. If we set the limit 2 than he can select only 2 game. Then if we select 5 than he can add maximum 5. Jere problem is if we select limit 2 we can add 5 game or whatever we want. there is not effect in the game after set a limit which is not acceptable.
Mgh 015 | Game time issue. | When we fix time for a game after finshed that time user can not access that game. It showing that the time is over. But here time is over notification only show when we access in the parents section. It does not affect in the game. the game is running even the time is over. Its a big issue. Please take care of it.
Mgh 016
Mgh 017
Mgh 018
Mgh 019
Mgh 020
Mgh 021 | [5 empty] | Updated
Mgh 022
Mgh 023
Mgh 024
Mgh 025
Mgh 026
Mgh 027
Mgh 028
Mgh 029
Mgh 030
Mgh 031 | [5 empty] | Updated
Mgh 032
Mgh 033
Mgh 034
Mgh 035
Mgh 036
Mgh 037
Mgh 038
Mgh 039
Mgh 040
Mgh 041
Mgh 042
Mgh 043
Mgh 044
Mgh 045
Mgh 046
Mgh 047
Mgh 048
Mgh 049
Mgh 050
Mgh 051
Mgh 052
Mgh 053
Mgh 054
Mgh 055
Mgh 056
Mgh 057
Mgh 058
Mgh 059
Mgh 060
Mgh 061
Mgh 062
Mgh 063
Mgh 064
Mgh 065
Mgh 066
Mgh 067
Mgh 068

## Feedback On apk 14
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Time out Problem | When we first enter the game & try to play a game it show time is over. Which is not right. After showing game is over the ok button also not working. Its a previous update issue which is not fixed. | 1
Mgh 002 | Parents cross button | In the parents verification page the cros button is not working. | 2 | Fixed
Mgh 003 | Buttons clash | In the parents page save & cross button are conflict with each other. I suggest to shift the save button behind the setting button. bit it does not changed. But you showing that its fixed. which is looks bad. | 3 | Fixed
Mgh 004 | Parents button access | user can easily access in the parents button when he play the game. During the play time if user click parents button he did not face any math problem. Without it he can access the parents button. | 4 | Fixed
Mgh 005 | Music setting button not working. | In the setting if we stop the music, it does not save. after passing the next page the music start working.. i try multiple time & same thing happening. | 5 | Fixed
Mgh 006 | Cross button vanished | When we go to the menu button than the cross button is missing. Please add this. | 6 | Fixed
Mgh 007 | elements wrong placement | In the languaage easy game porbo 1 porjai 5 elemets take wrong place | 7 | Fixed
Mgh 008 | elements wrong placement | In the languaage medium game porbo 2 porjai 2 elemets take wrong place | 8 | Element placed on mobile edge, will not consider as a drop.. User can still able to pick and drag to the destination.
Mgh 009 | elements wrong placement | In the languaage medium game porbo 2 porjai 5 elemets take wrong place | 9 | Element placed on mobile edge, will not consider as a drop.. User can still able to pick and drag to the destination.
Mgh 010 | Elements conflight | In the languaage medium game porbo 3 porjai 3 elemets conflight | 10 | Fixed
Mgh 011 | Elements conflight | In the languaage medium game porbo 3 porjai 4 elemets conflight | 11 | Fixed
Mgh 012 | Logical Mistake | In the parents button i do not set or add any game so in the game list it show none logicaly. But Here it shows all game. Please solve it. This is not right if you think logically. | 12 | Fixed
Mgh 013 | elements wrong placement | In the languaage hard game porbo 1 porjai 1 elemets conflight | 13 | Fixed
Mgh 014 | elements wrong placement | In the languaage hard game porbo 1 porjai 2 elemets conflight | 14 | Fixed
Mgh 015 | elements cut of | In the languaage hard game porbo 1 porjai 4 here the mark elements looks like cut of from the screan which is not acceted. | 15 | Fixed
Mgh 016 | Elements not aligned | In the languaage hard game porbo 1 porjai 5 here the right side marked elements are not aligned & in the left side elements are cut off. | 16 | Fixed
Mgh 017 | border missing. | In the languaage hard game porbo 2 porjai 3 here in the left side border is missing. | 17 | Fixed
Mgh 018 | elements wrong placement | In the matching easy game porbo 2 porjai 4 elemets took wrong place. | 18 | Element placed on mobile edge, will not consider as a drop.. User can still able to pick and drag to the destination.
Mgh 019 | elements wrong placement | In the matching easy game porbo 3 porjai 2 elemets took wrong place. | 19 | Fixed
Mgh 020 | elements wrong placement | In the matching easy game porbo 3 porjai 4 elemets took wrong place. | 20 | Fixed
Mgh 021 | Elements conflight | In the matching medium game porbo 1 porjai 1 two elements conflight | 21 | Fixed |  | Updated
Mgh 022 | Elements conflight | In the matching medium game porbo 1 porjai 2 two elements conflight | 22 | Fixed
Mgh 023 | Elements conflight | In the matching medium game porbo 1 porjai 3 two elements conflight | 23 | Fixed
Mgh 024 | Elements conflight | In the matching medium game porbo 1 porjai 4 two elements conflight | 24 | Fixed
Mgh 025 | Elements conflight | In the matching medium game porbo 1 porjai 5 two elements conflight | 25 | Fixed
Mgh 026 | Elements conflight | In the matching medium game porbo 2 porjai 1 two elements conflight | 26 | Fixed | please check this apk. it's only for Matching medium porbo2 projai 1.(this apk is only for this stage for test, ignore other bugs for this apk). show me it's schreenshot, if it's okay, i'll apply setting to all conflicted stages. | This time UI looks perfect but there is a tecnical issue. I put the elements wrong spot , it took place. Its issue which i find other stages also. But this time issue more bigger. This time i put the elements in the wrong place & it pass the stage also. Please Solve this. For UI it looks good. It better if you follow this pattern of UI in other stages also. | Issue VIdeo | don't worry about wrong spot, i'll fix...and i'll follow that pattern for conflict stages. | Great
Mgh 027
Mgh 028
Mgh 029
Mgh 030
Mgh 031 | [5 empty] | Updated
Mgh 032
Mgh 033
Mgh 034
Mgh 035
Mgh 036
Mgh 037
Mgh 038
Mgh 039
Mgh 040
Mgh 041
Mgh 042
Mgh 043
Mgh 044
Mgh 045
Mgh 046
Mgh 047
Mgh 048
Mgh 049
Mgh 050
Mgh 051
Mgh 052
Mgh 053
Mgh 054
Mgh 055
Mgh 056
Mgh 057
Mgh 058
Mgh 059
Mgh 060
Mgh 061
Mgh 062
Mgh 063
Mgh 064
Mgh 065
Mgh 066
Mgh 067
Mgh 068

## Feedback On apk 15
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | UI issue | In the language game hard porbo 1 porjai 4 two UI elements are conflight each other. | 1 | FIXED
Mgh 002 | UI issue | In the language game hard porbo 2 porjai 2 two UI elements are conflight each other. | 2 | FIXED
Mgh 003 |  | In the language game hard porbo 2 porjai 4 elements took wrong place. | 3
Mgh 004 |  | In the language game hard porbo 3 porjai 1 two UI elements are conflight each other. | 4 | FIXED
Mgh 005 |  | In the language game hard porbo 3 porjai 2 two UI elements are conflight each other. | 5 | FIXED
Mgh 006 |  | In the language game hard porbo 3 porjai 3 two UI elements are conflight each other. | 6 | FIXED
Mgh 007 |  | In the language game hard porbo 3 porjai 4 two UI elements are conflight each other. | 7 | FIXED
Mgh 008 |  | In the language game hard porbo 3 porjai 5 two UI elements are conflight each other. | 8 | FIXED
Mgh 009 |  | Music setting button is not work properly. When i music off then close the app & again enter app music start but in setting it shows music of. Which not acceptable. It should off until user do not turn it on. |  | FIXED
Mgh 010 |  | Every time i open the game click the play button. it shows a parents button pop up. Which is new issue arise. |  | FIXED
Mgh 011 |  | With out the parents button set i can play the game by crossing the button. Which is not accept. |  | Bcz, we've set some default setting for users, if not parents and click on parants button, then user can skip the parants setting just clicking on cross.
Mgh 012 |  | In the parents setting page the time limit is not working. Please check the issue.
Mgh 013 |  | In the matching game easy porbo 1 porjai 3 two UI elements are conflight each other. | 13 | FIXED
Mgh 014 |  | In the matching game easy porbo 1 porjai 5 two UI elements are conflight each other. | 14 | FIXED
Mgh 015 |  | In the matching game easy porbo 1 porjai 5 two UI elements are took wrong place | 15 | FIXED
Mgh 016 |  | I can not access in the matching game medium. i can access other game but does not entry in the medium. | 16 | FIXED
Mgh 017 |  | In the matching game hard porbo 2 porjai 2 two UI elements are conflight & there is a little gap also there. when i put the elements then elements should like proper. | 17 | FIXED
Mgh 018 |  | In the matching game hard porbo 2 porjai 4 two UI elements are conflight | 18 | FIXED
Mgh 019 |  | In the matching game hard porbo 2 porjai 5 two UI elements are conflight | 19 | FIXED
Mgh 020 |  | In the matching game hard porbo 2 porjai 5 two UI elements are conflight. It conflight with the pop up also | 20 | FIXED
Mgh 021 |  | In the matching game hard porbo 3 porjai 1-4 in every porjai there is common issue that one tree elements some part looks like it goes far from the screan. This one pic mainly for every porjai of level 3 | 21 | FIXED
Mgh 022 |  | In the matching game hard porbo 3 porjai 5 two UI elements are conflight. | 22 | FIXED
Mgh 023 |  | In the outline game medium porbo 2 porjai 4 mark elements set in the wrong possition. | 23 | FIXED
Mgh 024 |  | In the outline game medium porbo 2 porjai 4 mark elements set in the wrong possition. | 24 | FIXED
Mgh 025 |  | In the outline game medium porbo 3 porjai 1 mark elements are conflight. | 25 | FIXED
Mgh 026 |  | In the outline game medium porbo 3 porjai 4 mark elements looks like seat on top of the table. Not grounded. | 26 | FIXED
Mgh 027 |  | In the outline game medium porbo 1 porjai 5 elements took wrong place. |  | FIXED
Mgh 028
Mgh 029
Mgh 030
Mgh 031
Mgh 032
Mgh 033
Mgh 034
Mgh 035
Mgh 036
Mgh 037
Mgh 038
Mgh 039
Mgh 040
Mgh 041
Mgh 042
Mgh 043
Mgh 044
Mgh 045
Mgh 046
Mgh 047
Mgh 048
Mgh 049
Mgh 050
Mgh 051
Mgh 052
Mgh 053
Mgh 054
Mgh 055
Mgh 056
Mgh 057
Mgh 058
Mgh 059
Mgh 060
Mgh 061
Mgh 062
Mgh 063
Mgh 064
Mgh 065
Mgh 066
Mgh 067
Mgh 068

## Feedback On apk 16
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | UI issue | In the language game easy after finshed the the 1st porbo the pop does not identify properly. the pop up show in the normal way. It does not show like pop up. | 1 | This are all previous issue....Pop up Fixed
Mgh 002 | Sound Issue | In the language game medium porbo 1 porjai 1 the warning sound is play one time. After that it does not play. |  | working fine here.
Mgh 003 |  | in the language medium game porbo 1 porjai 3 elements took wrong place | 3
Mgh 004 |  | in the language medium game porbo 1 porjai 3 elements took wrong place | 4
Mgh 005 |  | in the language medium game porbo 1 porjai 3 the direction sound play only one time |  | Fixed
Mgh 006 |  | in the language medium game porbo 1 porjai 5 elements took wrong place | 6 |  | please check apk-17, hope it will work
Mgh 007 |  | in the language medium game porbo 2 porjai 1 elements took wrong place | 7 |  | please check apk-17, hope it will work
Mgh 008 |  | in the language medium game porbo 2 porjai 1 elements took wrong place | 8 |  | please check apk-17, hope it will work
Mgh 009 |  | in the language medium game porbo 2 porjai 1 elements took wrong place | 9 |  | please check apk-17, hope it will work
Mgh 010 |  | in the language medium game porbo 2 porjai 1 elements took wrong place | 10 |  | please check apk-17, hope it will work
Mgh 011 |  | in the language medium game porbo 2 porjai 2 elements took wrong place | 11 | Fixed | please check apk-17, hope it will work
Mgh 012 |  | in the language medium game porbo 2 porjai 2 elements took wrong place | 12 |  | please check apk-17, hope it will work
Mgh 013 |  | in the language medium game porbo 2 porjai 3 sound issue. It comes late. when i click the sound it start after some time. |  |  | please check apk-17, hope it will work
Mgh 014 |  | in the language medium game porbo 2 porjai 3 elements took wrong place | 13 |  | please check apk-17, hope it will work
Mgh 015 |  | in the language medium game porbo 2 porjai 3 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 14 |  | please check apk-17, hope it will work
Mgh 016 |  | in the language medium game porbo 2 porjai 4 sound issue. It comes late. when i click the sound it start after some time.
Mgh 017 |  | in the language medium game porbo 2 porjai 4 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 15 | Apk-2 | Apk-1 | look this video. i test this multiple device . I find same type of issue. If you want i can share those video also. Please test with different device & update device also. | Apk 2 update Apk 2 has still issue, not looking good. Need to work. | Apk 3 update. i found those issue still. | Apk 4 update. I am using androiad 13 . finding issues continues. Are test those thing with androiad 13 device. | APK3 | apk-4 | test now apk-5 | Apk 5 update The new Ui looks good. looks in better shape no doubt but unfortuently sorry to say the main bug still not fixed. | please let me know device name which is facing the issue, company and model.so i can ensure the reason behind the bug | Realme C55. | please test in one of them device. and let me know | pixel test report Device Name: Pixel 6a Android version : 14
Mgh 018 |  | in the language medium game porbo 2 porjai 5 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 16 |  | please check apk-17, hope it will work
Mgh 019 |  | in the language medium game porbo 3 porjai 1 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 17 |  | please check apk-17, hope it will work
Mgh 020 |  | in the language medium game porbo 3 porjai 2 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 18 |  | please check apk-17, hope it will work
Mgh 021 |  | in the language medium game porbo 3 porjai 3 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 19 |  | please check apk-17, hope it will work
Mgh 022 |  | in the language medium game porbo 3 porjai 4 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 20 |  | please check apk-17, hope it will work
Mgh 023 |  | in the language medium game porbo 3 porjai 5 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 21 |  | please check apk-17, hope it will work
Mgh 024 |  | in the language hard game porbo 1 porjai 1 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 22 |  | please check apk-17, hope it will work
Mgh 025 |  | in the language hard game porbo 1 porjai 2 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 23 | There is a common pattern of this issues. All the border line area elements are fixed there . Please check it. this issue repeats in every stages. | please check apk-17, hope it will work
Mgh 026 |  | in the language hard game porbo 1 porjai 3 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. | 24 |  | please check apk-17, hope it will work
Mgh 027 |  | in the language hard game porbo 1 porjai 4 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. |  |  | please check apk-17, hope it will work
Mgh 028 |  | in the language hard game porbo 1 porjai 5 elements took wrong place. All elements took wrong place. All of this issue are previous issue which are rise again. |  |  | please check apk-17, hope it will work
Mgh 029
Mgh 030
Mgh 031
Mgh 032
Mgh 033
Mgh 034
Mgh 035
Mgh 036
Mgh 037
Mgh 038
Mgh 039
Mgh 040
Mgh 041
Mgh 042
Mgh 043
Mgh 044
Mgh 045
Mgh 046
Mgh 047
Mgh 048
Mgh 049
Mgh 050
Mgh 051
Mgh 052
Mgh 053
Mgh 054
Mgh 055
Mgh 056
Mgh 057
Mgh 058
Mgh 059
Mgh 060
Mgh 061
Mgh 062
Mgh 063
Mgh 064
Mgh 065
Mgh 066
Mgh 067
Mgh 068

## Feedback On apk 17
No. | Issue Name | Issue Details | image/video link | Developer Status | Tester | Comments | APK Build Version | comments
Mgh 001 | Game complete button | The game complete button is continiuos counting. when i get out from it then in it start counting from start & it continue. Please check this issue
Mgh 002
Mgh 003
Mgh 004
Mgh 005
Mgh 006
Mgh 007
Mgh 008
Mgh 009
Mgh 010
Mgh 011
Mgh 012
Mgh 013
Mgh 014
Mgh 015
Mgh 016
Mgh 017
Mgh 018
Mgh 019
Mgh 020
Mgh 021
Mgh 022
Mgh 023
Mgh 024
Mgh 025
Mgh 026
Mgh 027
Mgh 028
Mgh 029
Mgh 030
Mgh 031
Mgh 032
Mgh 033
Mgh 034
Mgh 035
Mgh 036
Mgh 037
Mgh 038
Mgh 039
Mgh 040
Mgh 041
Mgh 042
Mgh 043
Mgh 044
Mgh 045
Mgh 046
Mgh 047
Mgh 048
Mgh 049
Mgh 050
Mgh 051
Mgh 052
Mgh 053
Mgh 054
Mgh 055
Mgh 056
Mgh 057
Mgh 058
Mgh 059
Mgh 060
Mgh 061
Mgh 062
Mgh 063
Mgh 064
Mgh 065
Mgh 066
Mgh 067
Mgh 068

## Tester area
SN | suggestion | Technical issue | Satus | UI issue | Image/ Vedio link
1 | If a user wants then he can on/off the sound.
2 | After successfully complete stage the animation should tell something to motivate to play the next stage |  |  |  | Sound for Stage 11 Expert Level in Language
3 | After a successfully complete the full stage needs achievement/ celebration animation
4 | In the matching game porbo 1 stage 2, there is a pic is missing, We have to change the UI.
5 | In the matching game porbo 1 stage 3, there are two pics that are missing, We have to change the UI.
6 | In the matching game porbo 1 stage 4, there are two pics that are missing, We have to change the UI.
7 | In the matching game porbo 1 stage 5, there are two pics that are missing, We have to change the UI.
8 | odds easy sound prb

## APK VCS
S No. | Build no | Link
1 | mgh-apk-003 | https://drive.google.com/file/d/1yUMIjtyP0aUDfFdik6_L-SyV53DeOMmr/view
2 | Mugdho_Update.apk | https://drive.google.com/file/d/1yUMIjtyP0aUDfFdik6_L-SyV53DeOMmr/view?usp=share_link
3 | mgh-apk-005 | https://drive.google.com/file/d/1QauMrMKbWOEmrZo6QreJXHObMNpO2LXo/view?usp=share_link
4 | mgh-apk-006 | https://drive.google.com/file/d/1M1yIKXx8b6tLBU0MoXWjQ9MHcihGk-5I/view?usp=share_link
5 | mgh-apk-007 | https://drive.google.com/file/d/1h-7n1vabMhV9HqH_FL_MrOFjeGEt9KD0/view?usp=share_link
6 | mgh-apk-008 | https://drive.google.com/file/d/1P5QijZot7B35z05N6klkTmwwyw31KK0U/view?usp=share_link
7 | mgh-apk-009 | Waiting For update apk(90% bug fixed)
8 | mgh-apk-009 | https://drive.google.com/file/d/1TUW29H-CX7SGbKzE9COWqG3GCA1W5AvP/view?usp=share_link
9 | mgh-apk-010 | https://drive.google.com/file/d/10yrq591q1T-zV6-jA9dgTZRaeNEAkGf3/view?usp=share_link
10 | mgh-apk-11 | https://drive.google.com/file/d/1c3PplMiXRYlo9y2mn1nYvUwZBw7GcXao/view?usp=share_link
11 | mgh-apk-012 | https://drive.google.com/file/d/1DnWewjD5rORX4Cq7Fxt4lxhtu7nnFkhH/view?usp=share_link
12 | mgh-apk-013 | https://drive.google.com/file/d/19o4SHikshqdvMlnQf8XKye8fmN57su1u/view?usp=share_link
13 | mgh-apk-014 | https://drive.google.com/file/d/1I70js7tNCOYPZbeqwUMqiAExiHp7Mi_V/view?usp=share_link
14 | mgh-apk-015 | https://drive.google.com/file/d/1DsAiLjyilw8LLO2BAeoYYBcueIxOTflz/view?usp=share_link
14 | mgh-apk-016 | https://drive.google.com/file/d/1qLrbIO6Byq7jrnC31jL4iouqoGq6zHnT/view?usp=sharing
15 | mgh-apk-017 | https://drive.google.com/file/d/1xDf8IzIImCSQ-rcyj3ELTqhwNNoWvPuy/view?usp=sharing
16 | mgh-apk-018 | https://drive.google.com/file/d/1zdV-bDnAYzNygfwumg-1uxq1-3o-Z6Bd/view?usp=sharing